## Use Case Template
Project Title: Minesweeper Release #: 2.0.0 Sprint #: 2
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
0 | Make every Gameboard component into a partial view | As a user I would like to be able to play Minesweeper without Refreshing the Page | Play without refreshing the page | I can have a more seamless experience | 2hr | Ali Cooper
1 | Ajax Gameboard
2 | Accurate timer | As a user I would like to play Minesweeper with a better functioning timer so that I can play with a more accurate second count | Play with accurate timer |  | .5hr | Ali Cooper