## Use Case Template
Project Title: Minesweeper Release #: 3.0.0 Sprint #: 3
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
0 | Make every Gameboard component into a partial view | As a developer, I would like to have a more modular codebase so that I can re use pieces of code | Have a more modular codebase | I can reuse pieces of code | 3hr | Ali Cooper
1 | Ajax Gameboard | As a user I would like to be able to play Minesweeper without Refreshing the Page so that I can hae a more consistent experince | Play Minesweeper | I can have a more consistent experience | 1hr | Ali Cooper
2 | Accurate timer | As a user I would like to play Minesweeper with a better functioning timer so that I can play with a more accurate second count | Play with an accurate timer | I can have an accurate representation of time | .5hr | Ali Cooper
3 | Save/Resume Functionality | As a user, I would like to be able to save/resume my board so that I can play the game at a later time | save/resume my board | I can play the game at a later time | 3hr | Ali Cooper
4 | REST Service | As a user, I would like to be able to use a rest service, so that I can access player statistics | use a rest service | I can access player statistics | .15hr | Ali Cooper